## Gantt Chart & Tasks
Phase | Task | Start Date | End Date | Duration (Days) | Assigned Roles
Assessment & Planning | Inventory All Servers | 2025-06-24 | 2025-06-29 | 5 | Infra Lead, Security
Assessment & Planning | Define Business Objectives | 2025-06-29 | 2025-07-02 | 3 | Project Manager, Executive Sponsor
Assessment & Planning | Assess Migration Readiness | 2025-07-02 | 2025-07-06 | 4 | Cloud Architect
Assessment & Planning | Classify Workloads | 2025-07-06 | 2025-07-09 | 3 | Cloud Architect, Infra Lead
Assessment & Planning | Design Target Azure Architecture | 2025-07-09 | 2025-07-13 | 4 | Cloud Architect
Assessment & Planning | Create Migration Plan | 2025-07-13 | 2025-07-17 | 4 | Project Manager, Cloud Architect
Proof of Concept | Select 1–2 Non-Critical Servers | 2025-07-17 | 2025-07-19 | 2 | Project Manager, Infra Lead
Proof of Concept | Test Azure Migrate Tooling | 2025-07-19 | 2025-07-22 | 3 | Cloud Engineer
Proof of Concept | Validate Dependencies | 2025-07-22 | 2025-07-24 | 2 | Security, Network
Proof of Concept | Gather Stakeholder Feedback | 2025-07-24 | 2025-07-26 | 2 | Project Manager
Pre-Migration Preparation | Configure Azure Landing Zone | 2025-07-26 | 2025-07-30 | 4 | Cloud Architect, Security
Pre-Migration Preparation | Set Up Infrastructure | 2025-07-30 | 2025-08-04 | 5 | Cloud Engineer
Pre-Migration Preparation | Establish Connectivity | 2025-08-04 | 2025-08-08 | 4 | Network
Pre-Migration Preparation | Backup and Snapshot On-Prem Servers | 2025-08-08 | 2025-08-10 | 2 | Infra Lead
Pre-Migration Preparation | Schedule and Communicate Downtime Windows | 2025-08-10 | 2025-08-11 | 1 | Project Manager
Migration Execution | Migrate in Batches | 2025-08-11 | 2025-08-21 | 10 | Cloud Engineer, Infra Lead
Migration Execution | Validate Post-Migration | 2025-08-21 | 2025-08-24 | 3 | QA, Cloud Engineer
Migration Execution | Monitor Logs & Metrics | 2025-08-24 | 2025-08-27 | 3 | Cloud Engineer
Migration Execution | Update DNS and Redirect Traffic | 2025-08-27 | 2025-08-29 | 2 | Network
Migration Execution | Decommission On-Prem Servers | 2025-08-29 | 2025-08-31 | 2 | Infra Lead
Optimization & Handoff | Rightsize Resources | 2025-08-31 | 2025-09-02 | 2 | Cloud Architect
Optimization & Handoff | Set Up Auto-Scaling & Backup | 2025-09-02 | 2025-09-05 | 3 | Cloud Engineer
Optimization & Handoff | Document Everything | 2025-09-05 | 2025-09-08 | 3 | Project Manager
Optimization & Handoff | Train Internal Teams | 2025-09-08 | 2025-09-10 | 2 | Project Manager
Optimization & Handoff | Operationalize Monitoring & Support | 2025-09-10 | 2025-09-12 | 2 | Cloud Engineer, Support Team

## RACI Matrix
Task | Role | RACI
Inventory All Servers | Infra Lead | Responsible
Inventory All Servers | Security | Responsible
Define Business Objectives | Project Manager | Accountable
Define Business Objectives | Executive Sponsor | Responsible
Assess Migration Readiness | Cloud Architect | Responsible
Classify Workloads | Cloud Architect | Responsible
Classify Workloads | Infra Lead | Responsible
Design Target Azure Architecture | Cloud Architect | Responsible
Create Migration Plan | Project Manager | Accountable
Create Migration Plan | Cloud Architect | Responsible
Select 1–2 Non-Critical Servers | Project Manager | Accountable
Select 1–2 Non-Critical Servers | Infra Lead | Responsible
Test Azure Migrate Tooling | Cloud Engineer | Responsible
Validate Dependencies | Security | Responsible
Validate Dependencies | Network | Responsible
Gather Stakeholder Feedback | Project Manager | Accountable
Configure Azure Landing Zone | Cloud Architect | Responsible
Configure Azure Landing Zone | Security | Responsible
Set Up Infrastructure | Cloud Engineer | Responsible
Establish Connectivity | Network | Responsible
Backup and Snapshot On-Prem Servers | Infra Lead | Responsible
Schedule and Communicate Downtime Windows | Project Manager | Accountable
Migrate in Batches | Cloud Engineer | Responsible
Migrate in Batches | Infra Lead | Responsible
Validate Post-Migration | QA | Responsible
Validate Post-Migration | Cloud Engineer | Responsible
Monitor Logs & Metrics | Cloud Engineer | Responsible
Update DNS and Redirect Traffic | Network | Responsible
Decommission On-Prem Servers | Infra Lead | Responsible
Rightsize Resources | Cloud Architect | Responsible
Set Up Auto-Scaling & Backup | Cloud Engineer | Responsible
Document Everything | Project Manager | Accountable
Train Internal Teams | Project Manager | Accountable
Operationalize Monitoring & Support | Cloud Engineer | Responsible
Operationalize Monitoring & Support | Support Team | Responsible